## Slide 2: Road Transportation Systems Engineering Development in the Sub-Saharan Africa – Modern EU Master Programme & Capacity Building

## Slide 4: Exercise 11
Planning asphalt compaction under hot conditions
Group exercise | Estimated duration: 90 minutes
Topic: Asphalt layer compaction, roller types, temperature, density control
Local context: Road section near Douala port, Cameroon
PowerPoint-ready classroom exercise
AfroTrans — Road Construction | Exercise 11
MSc Road Transportation Systems Engineering

## Slide 5: Slide 2. Learning objectives
Asphalt layer compaction, roller types, temperature, density control | Road section near Douala port, Cameroon
• Explain why asphalt must be compacted while hot.
• Select a roller sequence.
• Identify factors affecting mat temperature.
• Propose density control measures.
AfroTrans — Road Construction | Exercise 11
MSc Road Transportation Systems Engineering

## Slide 6: Slide 3. Background / case study
Asphalt layer compaction, roller types, temperature, density control | Road section near Douala port, Cameroon
• An asphalt layer is being placed near Douala port.
• The section carries heavy trucks and requires high density.
• The air temperature is high, but sudden rain showers are possible. Trucks from the plant sometimes arrive late.
• Assumed data for educational purposes.
AfroTrans — Road Construction | Exercise 11
MSc Road Transportation Systems Engineering

## Slide 7: Slide 4. Student task
Asphalt layer compaction, roller types, temperature, density control | Road section near Douala port, Cameroon
1. Select rollers for breakdown, intermediate and finish rolling.
2. Define the compaction sequence.
3. Identify risks if rolling starts too late.
4. Propose quality control checks.
5. Prepare a short field instruction for the roller crew.
AfroTrans — Road Construction | Exercise 11
MSc Road Transportation Systems Engineering

## Slide 8: Slide 5. Data / materials
Asphalt layer compaction, roller types, temperature, density control | Road section near Douala port, Cameroon
• Available rollers: static steel wheel roller, pneumatic-tired roller and vibratory roller.
Parameter | Value / condition
───────────────────────────────────────────┼───────────────────────────────────────────────────────────────────
Layer | Asphalt base layer
Compacted thickness | 80 mm
Target density | 96% of laboratory density
Initial mat temperature | 145°C
Minimum effective compaction temperature | assumed 90°C
Field risks | Delivery interruptions, variable temperature, edge cooling, rain
AfroTrans — Road Construction | Exercise 11
MSc Road Transportation Systems Engineering

## Slide 9: Slide 6. Work organisation
Asphalt layer compaction, roller types, temperature, density control | Road section near Douala port, Cameroon
• 20 min — group selects roller sequence.
• 20 min — identify risks.
• 25 min — prepare density control plan.
• 15 min — group presentations.
• 10 min — teacher feedback.
AfroTrans — Road Construction | Exercise 11
MSc Road Transportation Systems Engineering

## Slide 10: Slide 7. Expected answer / solution
Asphalt layer compaction, roller types, temperature, density control | Road section near Douala port, Cameroon
• Example compaction plan: breakdown rolling — vibratory roller while mat is hot.
• Intermediate rolling — pneumatic-tired roller for additional densification.
• Finish rolling — static steel wheel roller to remove marks and improve smoothness.
• Quality control: measure mat temperature, count roller passes, check density by cores or nuclear density gauge, inspect texture and smoothness, pay attention to joints and edges.
• Risks of late rolling: low density, high air voids, reduced durability, water infiltration and early distress.
AfroTrans — Road Construction | Exercise 11
MSc Road Transportation Systems Engineering

## Slide 11: Slide 8. Teacher notes
Asphalt layer compaction, roller types, temperature, density control | Road section near Douala port, Cameroon
• Observe whether students consider timing and temperature, and select rollers based on function.
• Typical mistakes: starting finish rolling too early; ignoring edge cooling; increasing binder content to compensate for poor density.
• Extension: how should the compaction plan change for a thin asphalt layer?
AfroTrans — Road Construction | Exercise 11
MSc Road Transportation Systems Engineering