## Slide 2: Road Transportation Systems Engineering Development in the Sub-Saharan Africa – Modern EU Master Programme & Capacity Building

## Slide 4: Project 04. Life-cycle timing
• Exercise type: Individual calculation + class debate
• Estimated duration: 45 minutes
• Course topic: pavement life-cycle and rehabilitation timing

## Slide 5: Learning objectives
• Interpret pavement condition decline over time.
• Compare early preventive maintenance with delayed rehabilitation.
• Perform a simple cost comparison.
• Defend maintenance timing using life-cycle logic.

## Slide 6: Background / case study
• A regional asphalt road is still in fair condition but deteriorating quickly.
• Decision-makers prefer postponing work because current damage is not yet dramatic.
• Engineers argue that early intervention is cheaper.
• Students prepare a technical argument for early maintenance.

## Slide 7: Student task
• 1. Compare two intervention strategies.
• 2. Calculate total cost per 10,000 m².
• 3. Identify non-monetary consequences of delay.
• 4. Prepare a two-sentence recommendation for the road authority.

## Slide 8: Data / materials
• Assumed data for educational purposes:
• Area: 10,000 m².
• Strategy A now: crack sealing + chip seal = 0.20 + 0.90 USD/m².
• Strategy B in 4 years: extensive repairs + HMA overlay = 1.50 + 5.80 USD/m².
• Expected condition if delayed: from fair to poor/very poor.
• Non-monetary factors: safety, travel time, road-user costs, market access.

## Slide 9: Work organisation
• Individual calculation: 10 min.
• Pair check: 5 min.
• Class debate: 20 min — “delay” versus “maintain now”.
• Teacher synthesis: 10 min — life-cycle principles.

## Slide 10: Expected answer / solution
• Strategy A: (0.20 + 0.90) × 10,000 = 11,000 USD.
• Strategy B: (1.50 + 5.80) × 10,000 = 73,000 USD.
• Delayed intervention costs about 6.6 times more in this simplified example.
• Recommendation: apply preventive maintenance now if structural capacity is still adequate; monitor condition after treatment.
• Non-monetary delay effects: reduced safety, higher vehicle operating costs, worse accessibility in rainy season.

## Slide 11: Teacher notes
• Observe whether students use area units correctly.
• Typical mistake: comparing unit costs but not total treated area.
• Key discussion point: early treatment is justified only if pavement is still structurally suitable.
• Extension: include discounting or uncertainty in remaining pavement life.