## Slide 2: Road Transportation Systems Engineering Development in the Sub-Saharan Africa – Modern EU Master Programme & Capacity Building

## Slide 4: Laboratory 05. Seasonal plan for an unpaved road
• Exercise type: Group planning exercise
• Estimated duration: 90 minutes
• Course topic: gravel and earth road maintenance

## Slide 5: Learning objectives
• Identify dry-season and rainy-season deterioration mechanisms.
• Select routine and periodic maintenance operations for unpaved roads.
• Sequence works in a practical annual plan.
• Relate maintenance to agricultural logistics and community access.

## Slide 6: Background / case study
• A 12 km laterite road connects farms with a local market.
• During the dry season, dust and corrugation reduce comfort and visibility.
• During the rainy season, rutting, potholes and slipperiness interrupt transport.
• A grader is available only twice per year; community labour can support drainage cleaning.

## Slide 7: Student task
• 1. List typical defects for dry and rainy seasons.
• 2. Select appropriate maintenance techniques: routine maintenance, light reprofiling, heavy reprofiling, reloading, reconstruction.
• 3. Prepare a 12-month maintenance calendar.
• 4. Identify what must be done before the rainy season.

## Slide 8: Data / materials
• Assumed road data:
• Length: 12 km; surface: laterite/gravel; traffic: agricultural trucks, motorcycles, pedestrians.
• Main defects: dust, raveling, corrugation, rutting, potholes, blocked ditches.
• Resources: one grader in March and October, local gravel stockpile, manual labour monthly.
• Rainy season assumed: April-June and September-November.

## Slide 9: Work organisation
• Group work: 30 min — defect table and calendar.
• Gallery walk: 30 min — compare plans.
• Class discussion: 20 min — common priorities.
• Teacher feedback: 10 min — realistic sequencing.

## Slide 10: Expected answer / solution
• Before rainy season: ditch and culvert cleaning, restore crown/crossfall, spot gravel, compact weak areas.
• Dry season: dust control where possible, grading of corrugations, vegetation control, safety checks near settlements.
• After heavy rains: inspect rutting, potholes, drainage erosion; apply routine local repairs.
• Heavy reprofiling or reloading is justified where rutting and loss of material are widespread.
• Reconstruction only for sections with persistent structural/geometric failure.

## Slide 11: Teacher notes
• Observe whether students schedule work before rather than after predictable rainfall.
• Typical mistake: proposing only one annual grading operation.
• Key discussion point: routine maintenance protects previous investment.
• Extension: ask how the plan changes with school bus service or mining trucks.